## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | 1 | Develop secure registration and login (NextAuth + bcrypt) so each research workspace stays private | Must | - | Gaurav | 3- Completed
1 | 1 | 2 | Develop document upload (PDF/TXT) with size caps and a searchable document library | Must | 1 | Gaurav | 3- Completed
1 | 1 | 3 | Develop a dashboard summarising documents, sessions, reports and risk flags | Should | 2 | Gaurav | 3- Completed
2 | 2 | 4 | Build a pipeline that parses, chunks and indexes uploaded filings for search (Document Agent) | Must | 2 | Gaurav | 3- Completed
2 | 2 | 5 | Extract financial metrics from filings, storing the exact source line as evidence (Extraction Agent) | Must | 4 | Gaurav | 3- Completed
2 | 2 | 6 | Identify red-flag risks in filings with exact quotes and severity levels (Red Flag Agent) | Must | 4 | Gaurav | 3- Completed
3 | 3 | 7 | Build a research Q&A agent that answers questions with [S1] citations users can verify | Must | 5 | Gaurav | 3- Completed
3 | 3 | 8 | Add optional semantic search (embeddings) with automatic keyword fallback | Could | 4 | Gaurav | 3- Completed
3 | 3 | 9 | Generate structured analysis reports (executive summary, key financials, risks, recommendations) | Must | 5 | Gaurav | 3- Completed
4 | 4 | 10 | Benchmark two companies on a like-for-like fiscal basis with period-mismatch warnings | Must | 5 | Gaurav | 3- Completed
4 | 4 | 11 | Validate uploads: reject non-financial files and name the detected wrong type (Validation Agent) | Must | 2 | Gaurav | 3- Completed
4 | 4 | 12 | Answer general questions with clearly-labelled unverified general knowledge | Should | 7 | Gaurav | 3- Completed
5 | 5 | 13 | Execute the unit test plan and close all tracked defects before release | Must | 12 | Gaurav | 3- Completed
5 | 5 | 14 | Deploy the application live with documentation and demo material | Should | 13 | Gaurav | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 | 1 | Set up Next.js + TypeScript project with Drizzle ORM and Postgres schema (12 tables) | Aug 20th | Aug 23rd | Gaurav | Coding | 3- Completed | 12
1 | 2 | Implement NextAuth credentials login with bcrypt hashing and session handling | Aug 24th | Aug 28th | Gaurav | Coding | 3- Completed | 10
2 | 3 | Build document upload API (PDF/TXT) with 4.5MB size cap and file type checks | Aug 28th | Aug 30th | Gaurav | Coding | 3- Completed | 8
2 | 1900-01-03 | Build document library UI with processing status badges | Aug 30th | Sep 1st | Gaurav | Coding | 3- Completed | 6
3 | 1900-01-04 | Create dashboard cards for documents, sessions, reports and risk flags | Sep 1st | Sep 2nd | Gaurav | Design | 3- Completed | 6
1 | 1900-01-05 | Seed script, demo account and first unit test suites | Sep 2nd | Sep 2nd | Gaurav | Testing | 3- Completed | 4
SPRINT 2 BACKLOG
4 | 1900-01-06 | Document Agent: parse, chunk and index uploaded filings into document_chunks | Sep 3rd | Sep 6th | Gaurav | Coding | 3- Completed | 12
5 | 1900-01-07 | Extraction Agent: prompt and JSON schema for financial metrics with evidence quotes | Sep 6th | Sep 9th | Gaurav | Coding | 3- Completed | 12
5 | 1900-01-08 | Save financial metrics to database with exact source line as evidence | Sep 9th | Sep 11th | Gaurav | Coding | 3- Completed | 8
6 | 1900-01-09 | Red Flag Agent: detect risk flags with severity levels and exact quotes | Sep 11th | Sep 14th | Gaurav | Coding | 3- Completed | 10
4 | 1900-01-10 | Orchestrator pipeline wiring with agent_logs entry for every stage | Sep 14th | Sep 15th | Gaurav | Coding | 3- Completed | 6
6 | 1900-01-11 | UI panels for metrics and risk flags with evidence viewer | Sep 15th | Sep 16th | Gaurav | Design | 3- Completed | 6
SPRINT 3 BACKLOG
7 | 1900-01-12 | Research Agent: hybrid retrieval (semantic + keyword) with [S1] style citations | Sep 17th | Sep 21st | Gaurav | Coding | 3- Completed | 12
7 | 1900-01-13 | Research chat UI showing cited passages and source snippets | Sep 21st | Sep 23rd | Gaurav | Coding | 3- Completed | 8
8 | 1900-01-14 | Semantic search (embeddings) integration with automatic keyword fallback | Sep 23rd | Sep 25th | Gaurav | Coding | 3- Completed | 8
9 | 1900-01-15 | Report Agent: executive summary, key financials, risk analysis, recommendations | Sep 25th | Sep 28th | Gaurav | Coding | 3- Completed | 12
9 | 1900-01-16 | Report viewer and export in the reports page | Sep 28th | Sep 29th | Gaurav | Coding | 3- Completed | 6
7 | 18 | Research answer grounding checks and citation validation testing | Sep 29th | Sep 30th | Gaurav | Testing | 3- Completed | 6
SPRINT 4 BACKLOG
10 | 19 | Benchmark Agent: like-for-like fiscal period comparison with mismatch warnings | Oct 1st | Oct 5th | Gaurav | Coding | 3- Completed | 12
10 | 20 | Benchmark comparison UI with side-by-side metrics table | Oct 5th | Oct 7th | Gaurav | Coding | 3- Completed | 6
11 | 21 | Validation Agent: financial-document scoring and wrong-type rejection (422) | Oct 7th | Oct 10th | Gaurav | Coding | 3- Completed | 12
11 | 22 | Validation messages naming the detected wrong type (resume, invoice, recipe) | Oct 10th | Oct 11th | Gaurav | Design | 3- Completed | 4
12 | 23 | General-knowledge answering mode with clearly labelled unverified answers | Oct 11th | Oct 12th | Gaurav | Coding | 3- Completed | 6
3 | 24 | Agent Activity feed on dashboard (per-agent view) | Oct 12th | Oct 13th | Gaurav | Coding | 3- Completed | 6
13 | 25 | Unit test cases for all agents and utility modules | Oct 13th | Oct 14th | Gaurav | Testing | 3- Completed | 8
SPRINT 5 BACKLOG
13 | 26 | Execute full unit test plan (18 cases) and record results | Oct 15th | Oct 16th | Gaurav | Testing | 3- Completed | 8
13 | 27 | Defect tracker: fix and close all logged defects before release | Oct 16th | Oct 17th | Gaurav | Coding | 3- Completed | 10
14 | 28 | Deploy application to Render (build, start, environment variables) | Oct 17th | Oct 18th | Gaurav | Deployment | 3- Completed | 6
14 | 29 | Prepare final documentation and project report | Oct 18th | Oct 19th | Gaurav | Documentation | 3- Completed | 8
14 | 30 | Demo script, team presentation and final submission | Oct 19th | Oct 20th | Gaurav | Documentation | 3- Completed | 6
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | Aug 27th | Guidelines and setup to begin working on the document upload pipeline | Begin the work on schema, login and upload
2 | Sep 10th | Discussing outcomes from Sprint 1; file parsing errors in the Document Agent | Make corrections to the pipeline and begin Extraction Agent work
3 | Sep 24th | Discussing outcomes from Sprint 2; research answers showing 0 cited passages | Fix retrieval with hybrid search and start Report Agent work
4 | Oct 8th | Discussing previous sprint outcome and discuss goals for benchmark and validation | Make corrections to the Research Agent and start Validation Agent work
5 | Oct 16th | Finalise on the final UI and make any required corrections before release | Make final changes and corrections, deploy and submit documentation

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | Aug 20th | Sep 2nd | Gaurav | Code for the schema, login and upload |  |  | Setup completed, upload live
2 | 2 | Sep 3rd | Sep 16th | Gaurav | Building the Document and Extraction Agents | Code for the schema and login | Developing the UI | Metrics and risk flags shipped
3 | 3 | Sep 17th | Sep 30th | Gaurav | Building the Research and Report Agents | Building basic file parsing | Developing the UI | Citations fixed with hybrid search
4 | 4 | Oct 1st | Oct 14th | Gaurav | Exploring benchmark and validation logic | Building research without citations | Developing the UI | Validation rejects wrong files
5 | 5 | Oct 15th | Oct 20th | Gaurav | Building the test plan and deployment | Exploring benchmark approaches | Developing the UI | Deployed and documentation submitted