## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Self (QA) | Corrupted/scanned PDF crashed document processing with a raw stack trace instead of a user message | Sprint 2 | Gaurav | Logical | Added extraction guard in the upload route returning 'PDF extraction failed' with guidance | 7th Sep 2026 | Closed | Verified with corrupt sample PDF
2 | Self (QA) | AI-extracted metric values conflicted with values printed in the financial statements | Sprint 2 | Gaurav | Logical | Implemented mergeWithLocalMetrics: deterministic parser values override the AI | 13th Sep 2026 | Closed | Local value wins on conflict
3 | Self (QA) | Metrics were saved even when the evidence line did not contain the number | Sprint 2 | Gaurav | Logical | Added evidenceSupportsMetricValue gate; unsupported metrics are skipped | 14th Sep 2026 | Closed | Evidence stored per metric
4 | Self (QA) | A crashed pipeline job held a lock forever and blocked the job queue | Sprint 2 | Gaurav | Logical | 15-minute stale lock reclaim plus atomic claim (UPDATE ... WHERE status='queued') | 15th Sep 2026 | Closed | Retested with simulated crash
5 | Self (QA) | Research answers contained numbers with no verifiable source (hallucination risk) | Sprint 3 | Gaurav | Logical | Mandatory exact supporting quotes + numeric-token validation; unsupported claims dropped | 24th Sep 2026 | Closed | Citation accuracy verified
6 | Self (QA) | Misconfigured embeddings provider surfaced a raw error page to the user | Sprint 3 | Gaurav | User Interface | Embeddings made optional; status shows 'Disabled (optional)' and keyword search takes over | 27th Sep 2026 | Closed | Graceful degradation
7 | Mentor Review | Report narrative could repeat figures that were not present in the extracted data | Sprint 3 | Gaurav | Logical | Report prompts bound to stored metrics/flags; tables rendered by code from real numbers | 30th Sep 2026 | Closed | Numbers by code, prose by AI
8 | Self (QA) | Benchmark compared companies across different fiscal years without any warning | Sprint 4 | Gaurav | Logical | Period-compatibility guard added; mismatch shows a clear warning, missing metrics show N/A | 4th Oct 2026 | Closed | Like-for-like enforced
9 | Self (QA) | Wrong file types (resume, invoice, novel) were accepted and processed as financial documents | Sprint 4 | Gaurav | Logical | Built Validation Agent: structure scoring + typed wrong-type detectors; 422 with 'looks like: Resume/CV' style reason | 10th Oct 2026 | Closed | 10-document acceptance matrix
10 | Self (QA) | Short cover letters were falsely accepted by the Validation Agent (finance words density too high) | Sprint 4 | Gaurav | Logical | Scaled finance-vocabulary density by document length; anchored title patterns to line starts | 11th Oct 2026 | Closed | Cover letter now rejected
11 | Self (QA) | Dashboard Multi-Agent Pipeline panel did not list the new Validation Agent | Sprint 4 | Gaurav | Standards | Added Validation Agent card to the dashboard pipeline panel and document page summary | 12th Oct 2026 | Closed | UI consistent with agents
12 | Self (QA) | Questions naming a specific PDF searched all documents and returned no usable passages | Sprint 4 | Gaurav | Logical | Filename targeting: question naming a file searches only that document; filler words stripped | 13th Oct 2026 | Closed | Retrieval precision improved
13 | Self (QA) | Profit & loss questions retrieved boilerplate pages ('0 cited passages') instead of statements | Sprint 4 | Gaurav | Logical | Keyword scoring: stopword removal + financial-phrase expansion (P&L -> operations, income...) | 14th Oct 2026 | Closed | Retrieval quality fix
14 | Self (QA) | General questions (e.g. 'What is gross margin?') ended in a refusal dead-end message | Sprint 5 | Gaurav | User Interface | General-knowledge mode added with clear 'not verified' label + tip to ask about filings | 17th Oct 2026 | Closed | Trust model preserved
15 | Self (QA) | Agent Activity panel showed only Research Agent rows, hiding the rest of the team | Sprint 5 | Gaurav | User Interface | Panel now shows the latest activity entry per agent instead of raw newest rows | 18th Oct 2026 | Closed | Full team visible

## Sheet2
Logical
User Interface
Maintainability
Standards
Others